## Instructions
Description:
The Generic All-Hazards Risk Assessment and Planning Tool for Mass Gathering Events (“All-Hazards MG RA Tool”) aims to support Member States and mass gathering events organizers in identifying and mitigating potential all-hazard events that could impact their gathering and provide the basis for mass gatherings planning.
The tool is based on the principles of the World Health Organization’s Strategic Toolkit for Assessing Risk (STAR) as well as lessons learned identified from the COVID-19 Risk Assessment Tool for Mass Gatherings. The purpose of the All-Hazards MG RA tool is to identify hazards related to the event, assess and quantify the overall level of risk, and identify and account for precautionary measures that may reduce the risk, making the event safer.
The tool provides a systematic evidence-based approach to identifying and classifying priority risks; a description of the level of national preparedness and readiness to mitigate specific hazards; guidance on the implementation of a comprehensive and strategic risk assessment to inform preparedness and response plans ahead of the mass gathering; and an estimated assessment of the host country capacity to identify and respond to potential negative health impacts.
Details:
The tool includes the following tabs: 1. Overview of the Process; 2. General Information; 3. Describe the Mass Gathering; 4. Assessing the Risk Process; 5.Identifying Hazard; 6. Evaluating Likelihood; 7. Risk Score; 8. Determining Impact; 9. Precautionary Measures; 10. Risk Communications; and 11. Reviewer Sign Off.
By inputting details on the event and responding to mitigation statements, public health authorities and event organizers are presented with a list of priority hazard areas to be aware of, an overall risk score, and suggested mitigation techniques to incorporate in the preparedness plans for the event. By inputting details on the GOARN count capacity - or the relevant IHR States Parties Self-Assessment Annual Reporting (SPAR) indicator scores, event organizers will also gain an awareness of the country health system capacities to respond to an all hazard event.
The ‘Overview of the Process’ tab provides a brief description of the purpose, principles, steps, and methodology of the tool. Event organizers begin interacting with the tool in the ‘General Information’ tab. The primary purpose of this tab is for WHO to maintain records of which events utilized the tool. Sections include the mass gathering name, host country, region, date of the risk assessment, and the assessment team.
In the ‘Describe Your Mass Gathering’ tab, event organizers are asked to answer questions surrounding the main characteristics of the planned mass gathering. These questions are primarily centered on the basic facts of the event and the make up of the attendee and/spectator population. Answers to the questions in this tab and in the future tab ‘Identifying Hazard’ tab hold a weighted score – the higher the score, the riskier the event. Additionally, questions in this tab filter out questions in future tabs to reduce the number of questions event organizers have to answer throughout the tool.
In the ‘Assessing the Risk Process’ tab, event organizers are provided an overview of the curricular process of the tool. Event organizers are expected to utilize this tool multiple times as they implement mitigation measures to reduce their risk score.
Event organizers then move to the ‘Identifying the Hazard’ tool where they answer questions on the hazards most likely to require a response or most likely to contribute to negative health outcomes for the mass gathering. Considerations include type of hazard, health consequences, scale, and exposure. At the end of this set of questions, event organizers will be presented with a priority list of potential hazards. Categories include: epidemiological concerns (infectious disease outbreaks from person to person spread, not including sexually transmitted infections (STIs)), epidemiological concerns (STIs), epidemiological concerns (vector borne disease), non-infectious disease health threats (non-communicable diseases, excessive use of substances, injuries, stampedes, trampling), environmental concerns (frostbite, over-heating, poor air quality), CBRN threats, and food safety and/or clean water concerns.
In the ‘Evaluating Likelihood’ tab, event organizers are able to ‘buy down’ their risk from the previous tabs if they answer ‘yes’ to the mitigation measure statements. Mitigation measures are broken into the following categories: General factors, Venue factors, Behavioral factors, Epidemiological factors, CBRN and other security hazards, and Environmental factors.
Based on the inputs from the previous tabs, event organizers are now presented with a risk score which is plotted on a risk matrix – the axes are impact and likelihood. The risk score ranges from very low to very high. In addition to the risk score within the ‘Determining Impact’ tab, event organizers are also provided their SPAR score to help assess the host countries health care system capabilities if a threat occurred or if their SPAR score is older than two years, they will be asked to answer additional questions to get an estimation of capacities.
In the ‘Precautionary Measures’ tab, event organizers are presented with automatically populated WHO precautionary measures based on their ranked hazard areas. This is followed by the ‘Risk Communications’ tab which guides event organizers through building a comprehensive mass gathering communications plan including considerations on messaging various policy decisions and changes ahead of or during the mass gathering. Finally, in the ‘Review Sign Off’ tab, event organizers are presented with all the information in one place which they can print out and share with other members of the event organization team.
The All-Hazards Mass Gathering risk assessment exercise is finalized with the compilation of all the risk information summarized in one place. This can be printed-out and shared with other members of the risk assessment team and updated as necessary.
WHO/2023-Generic/Mass_gatherings_All_Hazards_RAtool/2023.1
© WHO 2023. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.

## Overview of Process
The risk-based approach articulated in the Generic All-Hazards Risk Assessment Tool for Mass Gathering Events (“MG RA Tool”) is based on the principles of the World Health Organization’s Strategic Toolkit for Assessing Risk (STAR) as well as methods identified for the COVID-19 Risk Assessment Tool for Mass Gatherings.
PURPOSE:
To identify the priorty hazards related to hosting the mass gathering and assess the risk level of the mass gathering for the local community/country. To identify and implement mitigation measures to buy down the risk and develop a preparedness plans for the mass gathering.
PRINCIPLES OF THE TOOL:
The development of this tool is compiled based on the following principles:
All-hazards approach: health emergency management policies, strategies and related programmes should be designed to address common issues with common capacities, supplemented by risk-specific capacities.
Whole-of-society approach: recognizing and promoting the participation and coordination of relevant stakeholders in health and other sectors at all levels of society. These key stakeholders are information-rich and contribute to effective risk assessment.
Health system approach: capturing risks from any hazards at all levels of the health system in a given country (primary, secondary and tertiary levels), as well as accounting for risks at the community, municipality, city, other subnational and national levels.
Risk-informed evidence compilation: Using primary or secondary data available in the country derived from research, assessments, surveillance, evaluations of previous emergencies, International Health Regulations (IHR 2005) monitoring, inclusive of the IHR State Party Self-Assessment Annual Reporting Tool (SPAR), meteorological profile description, and any other relevant data.
Transparency: Obtaining agreement across all stakeholders, including government authorities and partners, to build trust, enhance the acceptability of findings and drive their commitment to the implementation of actions and recommendations of the risk assessment and to timely communicate recommendations to mass gathering participants and the general public.
Building on these principles, the "MG RA Tool" supports mass gathering planners and stakeholders through a multi-step risk assessment process organized across corresponding modules:
Step 1: Describe your mass gathering to identify the prominent hazards of the event and risk areas
Step 2: Assessing the risk of the mass gathering (2A. Identifying hazards; 2B. Evaluating Likelihood; 2C. Calculating the Risk Score; 2D. Determining Impact)
Step 3: Identifying the precautionary measures to implement to mitigate risks
Step 4: Implement and communicate the mass gathering plan
Step 5: Repeat the risk assessment process regularly and finalize mass gathering plan
Step 6: Conduct evaluation and legacy activities after the completion of the event
METHODOLOGY:
Within each module, users will be asked to answer relevant questions about the event in question to the best of their knowledge. This process is intended to be iterative, drawing on existing data, expertise, and multisectoral coordinating mechanisms to identify relevant hazards, ascertain their likelihood of occurring, and estimate their potential impact on the mass gathering in question. Mass gathering event planners are encouraged to apply the "MG RA Tool" before, during, and after the event in question to ensure a holistic and comprehensive approach to assessing risks associated with naturally occurring, manmade, accidental, and/or deliberate hazards to population health and wellbeing.
WHO/2023-Generic/Mass_gatherings_All_Hazards_RAtool/2023.1
© WHO 2023. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.

## 1. Describe Your Mass Gathering
Step 1. Describe Your Mass Gathering
What are the main characteristics of your planned mass gathering?
Instuctions: For each question, input your answer to briefly address the question.
1. Mass Gathering Name
2. Host Country
3. WHO Region
4. Date of Risk Assessment
6. Description of Mass Gathering
5. Assessment Team Members and Role (i.e. leader etc.)
WHO/2023-Generic/Mass_gatherings_All_Hazards_RAtool/2023.1
© WHO 2023. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.

## 1a.Describe Your Mass Gathering (hidden)
Step 1: Describe your Mass Gathering
What are the main characteristics of your planned mass gathering?
Instuctions: For each question, select an answer from the dropdown options provided. All questions must be answer before proceeding to Step 2: Assessing the Risk of Your Mass Gathering
Action | Question | Answer | Numeric Score | Weight | Weighted Score
Please select the option that best describes the event.
Event
Unweight | Will the event be held indoors, outdoors, or utilize a hybrid approach that has a virtual component? | Hybrid format | 2 | 3 | 6
Unweight | How long will the gathering last (choose the most accurate answer possible)? | 1-7 days | 2 | 1 | 2
| Approximately how many individuals are expected to attend? | 1001-10000 | 1 | 2 | 2
Unweight | Will the mass gathering include spectators? | Info not available | 0 | 3 | 0
Unweight | Are there multiple venues for the mass gathering that the event organizers must incorporate in their plans? | NOT APPLICABLE | 1 | 3 | 3
Participants
Unweight | Will the gathering consist primarily of local participants (i.e., residents of the city/town in which the event will be held), national participants (i.e., residents of the country in which the event will be held, but not the city/town), or international participants (i.e., from jurisdictions outside of the host country)? | National attendees | 1 | 3 | 3
Unweight | Will national or international participants require on-site or other local accommodations during the event? | No | 0 | 1 | 0
Unweight | Will the mass gathering include vulnerable or at "high risk" participants or spectators (including staff and other relevant personnel) with risk factors for severe disease or health complications (e.g. people aged > 60 years and/or with comorbidities, disadvantaged groups)? | Don’t know | 0 | 3 | 0
Included | How will participants arrive at the event venue? | A mixture of the above | 1.5 | 2 | 3
Unweight | Are there conditions for entry into the gathering (e.g., registration, ticketing, invitation)? | Yes | 1 | -2 | -2
Included | Will participants gather at official event clubs or areas prior to, during, or after the event? | No | 0 | 3 | 0
Unweight | Do you anticipate that participants and/or external spectators will congregate informally outside the gathering venue (e.g., at bars, restaurants, religious institutions)? | No | 0 | 3 | 0
| Will food be provided during the mass gathering? | YES | 2 | 2 | 4

## 2. Assessing the Risk Process
WHO/2023-Generic/Mass_gatherings_All_Hazards_RAtool/2023.1
© WHO 2023. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
Step 2. ASSESSING THE RISK OF YOUR MASS GATHERING: PROCESS
*Adapted from the WHO Strategic Tool for Assessing Risks (STAR)
2A. Identifying the Hazard
What are the hazards most likely to require a response or most likely to contribute to negative health outcomes for the mass gathering?
Considerations include type of hazard, health consequences, scale and exposure. Outputs include:
Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including sexually transmitted infections (STIs))
Epidemiological Concerns (STIs)
Epidemiological Concerns (vector borne diseases)
Non-Infectious Disease Health Threats (non-communicable diseases, excessive use of substances, injuries, stampedes, trampling)
Environmental Concerns (frostbite, overheating, poor air quality)
CBRN Threats
Food Safety and/or Clean Water Concerns
2B. Evaluating the Likelihood
What is the likelihood that the identified hazards in Step 2A will occur during the mass gathering and require coordinated response to mitigate negative health outcomes?
Considerations include frequencies, seasonality and likelihood of the hazards. Outputs include mitigation statements and plans to reduce the likelihood of hazards.
2C. Generating the Risk Score
The questions and statements in Steps 2A and 2B are combined to determine the Risk Score of the mass gathering, depending on the hazards identified, and their likelihood of occurring.
The Risk Score is determined by a risk matrix combining the identified hazards and the likelihood of them occurring. Risk Scores range from very low, low, moderate, high, and very high.
2D. Determining the Impact
What are the likely impacts should a hazard occur during the mass gathering? What is the ability of the host country to respond to such a hazard to mitigate further coping capacity?
Considerations include severity of the hazard occurring, vulnerability of the population, and local coping capacity. Outputs include measuring the preparedness and health capacity level of the host city/country through analysis of:
After Action Reviews (AARs)
Intra Action Reviews (IARs)
Joint External Evaluation (JEEs)
National Action Plan for Health security (NAPHs)
IHR State Party Self-Assessment Annual Reporting Tool (SPAR) assessments
Other assessments

## 2A. Identifying Hazard
Step 2A: Identifying the Hazard
What are the hazards most likely to require a response or most likely to contribute to negative health outcomes for the mass gathering? Considerations include type of hazard, health consequences, scale and exposure.
Instuctions: For each question, select an answer from the dropdown options provided. According to the information provided, a list of priority hazards of concern for your mass gathering will be calculated at the bottom of the sheet. All questions must be answer before proceeding to Step 2B: Evaluating the Likelihood
Category | Questions | Answer | Numeric Score | Weight | Weighted Score | Identified Hazards Category:
General Factors | Will the gathering consist primarily of local attendees (i.e., residents of the city/town in which the event will be held), national attendees (i.e., residents of the country in which the event will be held, but not the city/town), or international attendees (i.e., from jurisdictions outside of the host country)? | International attendees | 2 | 5 | 10
| Will the mass gathering include spectators? | Info Unavailable | 2 | 4 | 8
| Will the mass gathering include international spectators? | INFO UNAVAILABLE | 2 | 4 | 8
| Will the mass gathering include vulnerable or at "high risk" attendees or spectators (including staff and other relevant personnel) with risk factors for severe disease or health complications (e.g. people aged > 60 years and/or with comorbidities, disadvantaged groups)? | Info Unavailable | 2 | 3 | 6
| If mass gathering will include vulnerable or at "high risk" attendees or spectators (including staff and other relevant personnel), what is the percentage that are expected to attend the event ? (Answer NOT APPLICABLE if the event will not include vulnerable or at "high risk" participants or spectators) | NOT APPLICABLE | 0 | 3 | 0
| Will participants be mostly standing, sitting, or engaging in mobile activity during the event? | Mostly standing | 1 | 3 | 3
| How long will the gathering last (choose the most accurate answer possible)? | 1-7 days | 2 | 3 | 6
Venue Factors | How will participants arrive at the event venue? | Transportation provided by the event organizers (e.g., shuttles) | 0 | 2 | 0
| Will the event be held indoors, outdoors, or utilize a hybrid approach that has a virtual component? | Outdoors | 1 | 5 | 5
| Are there conditions for entry into the gathering (e.g., registration, ticketing, invitation)? | Don't Know | 0 | 1 | 0
| Will national or international attendees require on-site or other local accommodations during the event? | Info Unavailable | 1 | 1 | 1
| Are there multiple venues for the mass gathering that the event organizers must incorporate in their plans? | INFO UNAVAILABLE | 1 | 3 | 3
| How will participants move between venues? | Info Unavailable | 2 | 2 | 4
| How much of the venue’s capacity will be utilized? (expressed as a percentage of full venue capacity)? | GREATER THAN 75% | 2 | 4 | 8
Behavioural Factors | Do you anticipate that event attendees and/or external spectators will congregate informally outside the gathering venue (e.g., at bars, restaurants, religious institutions)? | NOT APPLICABLE | 0 | 5 | 0
| Will participants gather at official event clubs or areas prior to, during, or after the event? | Not Applicable | 0 | 3 | 0 |  | *
| Do you anticipate that attendees will engage in recreational or illicit substance use (including injectable drugs), alcohol consumption, or physical violence/self harm? | YES | 2 | 4 | 8
| Do you anticipate that attendees will engage in unprotected sexual intercourse? | YES | 2 | 4 | 8
| Do you anticipate that attendees will engage in fasting or other dietary modifications? | YES | 2 | 3 | 6
| Do you anticipate that attendees will engage in singing, cheering, chanting, or other forms of collective vocalization at the venue or in connection to the mass gathering? | YES | 2 | 3 | 6
| Does the host country report a high use of illicit drug use, engagement of sex workers, or excessive drinking? | YES | 2 | 3 | 6
Epidemiological Factors | Has the host country reported any endemic diseases that may have a risk of further spread due to the nature of the planned gathering? | No | 0 | 5 | 0
| During previous mass gatherings, has the host country reported high burdens of vaccine-preventable diseases, diarrheal diseases, vector-borne diseases, sexually transmitted infections (STIs), respiratory diseases? | No | 0 | 10 | 0
| In the last year, has the host city reported high burdens of vaccine-preventable diseases, diarrheal diseases, vector-borne diseases, sexually transmitted infections (STIs), respiratory diseases? | INFO UNAVAILABLE | 2 | 10 | 20
| Are there any infectious diseases of concern in the home countries of attendees and/or spectators that present a risk of international spread due to the mass gathering? (Answer NOT APPLICABLE if there is no expected international participation) | NOT APPLICABLE | 0 | 5 | 0
| Will the gathering take place during the host country’s annual influenza season? (In temperate climates, annual influenza season occurs mainly during winter, while in tropical regions, influenza may occur throughout the year) | INFO UNAVAILABLE | 2 | 4 | 8
| Does the host country report high burdens of antimicrobial resistance? | YES | 2 | 3 | 6
| Has the host country reported a case of viral hemorrhagic fever (e.g., Ebola, Marburg, Crimean-Congo) in the past year? | INFO UNAVAILABLE | 2 | 2 | 4
| Does the host country report high rates of chronic diseases (e.g., cancer, cardiovascular disease, diabetes, chronic kidney disease, chronic respiratory disease, obesity, malnutrition)? | YES | 2 | 3 | 6
| Does the host country report high rates of road traffic injuries? | YES | 2 | 2 | 4
CBRN and Other Security Hazards | Has the host country experienced an outbreak of unknown origin or a deliberate infectious disease outbreak in the past year? | NO | 0 | 3 | 0
| Is the mass gathering considered a high profile/high visibility event where the threat of a deliberate CBRN event is a concern? | NO | 0 | 5 | 0
| Is there a reported moderate, high, or significant risk of a deliberate CBRN event occuring at the mass gathering? | NO | 0 | 5 | 0
| Are political, religious, gender, LGBTQ+, sport rivalry, or other tensions expected among the groups of participants? | No | 0 | 3 | 0
| Is the host country currently experiencing state-sponsored armed conflict (e.g., war, genocide), violent conflict associated with non-state actors (e.g., acts of terrorism, riots), strikes, or protests? | NO | 0 | 3 | 0
Environmental Factors | Does the host country report high levels of outdoor air pollution? | YES | 2 | 2 | 4
| Will attendees consume food and/or beverages that are prepared onsite at the venue? | No | 0 | 3 | 0
| Has the host country reported water borne disease outbreaks in the last year? | NO | 0 | 5 | 0
| Will attendees be exposed to harsh weather conditions during the gathering, such as extreme heat, cold, rain, snow, or storms? | NO | 0 | 5 | 0
| Will attendees come into contact with live animals, plants, and/or other introduced or invasive species at the venue? | No | 0 | 2 | 0
| Will participants be exposed to pyrotechnics, explosives, or other fire hazards at the venue? | NO | 0 | 1 | 0
| Will attendees handle or be in close proximity to firearms and ammunition (or other combat weapons) at the venue? | NO | 0 | 1 | 0
148
Hazard Categories:
Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs)
Epidemiological Concerns (STIs)
Epidemiological Concerns (vector borne disease)
Non-Infectious Disease Health Threats (noncommunicable diseases, excessive use of substances, injuries, stampedes, trampling)
Environmental Concerns (frostbite, overheating, poor air quality)
WHO/2023-Generic/Mass_gatherings_All_Hazards_RAtool/2023.1
Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs)
Epidemiological Concerns (STIs)
Epidemiological Concerns (vector borne disease)
Non-Infectious Disease Health Threats (noncommunicable diseases, excessive use of substances, injuries, stampedes, trampling)
Environmental Concerns (frostbite, overheating, poor air quality)
CBRN Threats
Food Safety and/or Clean Water Concerns
© WHO 2023. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.

## 2B. Evaluating Likelihood
Step 2B: Evaluating the Likelihood of the Hazard Occuring
What are the likelihood that the identified hazards will occur during the mass gathering and require a coordinated response to mitigate negative health outcomes? Considerations include frequencies, seasonality and likelihood of the hazards.
Instructions: For each statement, select an answer from the dropdown options provided. According to the information provided, the likelihood of a hazard of concern for your mass gathering will be calculated at the bottom of the sheet. All questions must be answered before proceeding to finding your Risk Score.
Category | Hazard Connection | Likelihood or Mitigation Statement | Answer | Score | Weight | Weighted Score | Identified Hazards Category:
General Factors | Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns (vector borne diseases) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) | Event organizers and other stakeholders involved in the mass gathering planning process are aware of general mass gathering preparedness best practices and recommendations to implement during the event. | Yes | 2 | 1 | 2
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns (STIs) Epidemiological Concerns (vector borne diseases) | Event organizers and other stakeholders inolved in the mass gathering planning process are aware of any disease outbreaks that may cause potential concern to the mass gathering (either in the host city/country or the city/country of participants). | No | 0 | 2 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns (STIs) Epidemiological Concerns (vector borne diseases) | The relevant mass gathering organizers and responsible staff are in coordination with local public health authorities and are commiting to using the latest available guidance on disease control and mass gathering preparedness. | No | 0 | 1 | 0
|  | There is a formal information-sharing process established between the mass gathering organizers and local/national public health authorities. | No | 0 | 1 | 0
|  | There is a formal information-sharing process established between the mass gathering organizers and other stakeholders (i.e. ministry of transport, ministry of foreign affairs, emergency services, law enforcement etc.), as needed. | No | 0 | 1 | 0
|  | The mass gathering organizers have collected any available information about the participants, staff, spectators etc. for the event (including countries of provenance, the epidemiological situation in those countries, individuals' health and personal information, data on behaviours, etc.) to gain a better understanding of the potential risks of disease spread or other health consequences during the event, and implement mitigation measures. | No | 0 | 1 | 0
|  | There are arrangements to activate a strategic health operations centre (SHOC) or other relevant event organizing structure in the case that there is a suspected disease outbreak or other health related hazard in connection to the mass gathering. | No | 0 | 1 | 0
|  | The mass gathering will restrict international participants from attending (either partially or fully). | No | 0 | 3 | 0
|  | The mass gathering will not allow spectators to attend. | No | 0 | 3 | 0
|  | The mass gathering will only allow local or national spectators to attend. | No | 0 | 2 | 0
|  | The mass gathering will be bound. | No | 0 | 2 | 0
|  | Event planners have procured event insurance. | Yes | 2 | 1 | 2
Venue Factors | Epidemiological Concerns (vector borne disease) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) Food Safety and/or Clean Water Concerns | The venue is in compliance with local fire hazard guidelines, flood prevention guidelines, and building codes. | NO | 0 | 2 | 0
| Epidemiological Concerns (vector borne disease) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) Food Safety and/or Clean Water Concerns | Indoor venues have windows and doors that are able to remain open to allow for additional air flow. | NO | 0 | 2 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concernts (vecton borne diseases) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) | A cleaning schedule has been developed to ensure the mass gathering venues and any equipment needed are clean and hygienic with respect to germ spread. | NO | 0 | 1 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns (vector borne diseases) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) | The venue facility has a defined occupancy policy that ensures indoor ventilation rate is met at any time. | NO | 0 | 2 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns (vector borne diseases) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) | The facility enables cross-side ventilation, in comparision to single side, for naturally-ventilated venues. | NO | 0 | 2 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns (vector borne diseases) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) | Rooms where participants and/or spectators will be gathered have HVAC systems using fresh outdoor air (preferable) or filtered air in comparison to an air conditioning (AC) system working with air recirculation for all indoor settings. | NO | 0 | 1 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns (vector borne diseases) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) | In the event that air recirculation is used, the HVAC system is equipped with minimum efficiency reporting value (MERV) 15 / ISO ePMI 70-80% or HEPA filter AND filters are cleaned and maintained according to manufactory recommendations. | NO | 0 | 1 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns (vector borne diseases) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) | If air cleaner is used, the system is equipped with minimum efficience reporting value (MERV) 14 / ISO ePMI 70-80% or HEPA filter AND filters are cleaned and maintained according to manufactory recommendations. | NO | 0 | 1 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns (vector borne diseases) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) | If air cleaner is used, the devise's clean air delivery rate (CADR) (m³/hr) covers the gap between the minimum requirement and the measured ventilation rate. | NO | 0 | 1 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns (vector borne diseases) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) | The exhausted air is managed correctly. Air should be exhausted directly to the outside, away from vents (air ducts), people and animals. | NO | 0 | 2 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns (vector borne diseases) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating)ther Condition Concerns (frostbite, over heating) Food Safety and/or Clean Water Concerns | Indoor temperatures will be monitored and adjusted as needed during the mass gathering. | Yes | 2 | 3 | 6
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns (vector borne diseases) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) | Plans for a safe evacuation from the venues have been developed and tested. | Yes | 2 | 3 | 6
|  | There are designated shuttles, cars, buses, or other vehicles for transporting participants to and from the venue. | No | 0 | 1 | 0
|  | There are physical barriers in the venue to limit the mixing of different groups (i.e. between sections or between the seated audience and the attendees/athletes/presenters etc.) | No | 0 | 2 | 0
|  | There are decals and/or signage in place to limit the mixing of people and encourage directional/one-way walkways. | No | 0 | 1 | 0
| Food Safety and/or Clean Water Concerns | There are appropriate measures in place for restaurants/food stands within the venue including running water, electricity, and temperature-appropriate storage. | No | 0 | 3 | 0
| Epidemiological Concerns (vector borne disease) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) Food Safety and/or Clean Water Concerns | There is designated seating for spectators. | No | 0 | 2 | 0
Behavioural Factors | Epidemiological Concerns (STIs) | Pamphlets or other educational materials have been handed to all participants prior to the mass gathering to promote safe sex practices. | No | 0 | 1 | 0
| Epidemiological Concerns (STIs) | Event organizers have ensured that condoms are easily accessible to attendees and participants. | NOT APPLICABLE | 2 | 2 | 4
| Non Infectious Disease Health Threats (injuries, stampedes, trampling) | There are measures in place to limit excessive alcohol and/or drug consumption at the event venue. | NOT APPLICABLE | 2 | 3 | 6
|  | There are measures in place to limit excessive alcohol and/or drug consumption in the areas close to the venue(s). | NOT APPLICABLE | 2 | 3 | 6
|  | There are measures in place to ban smoking. | NOT APPLICABLE | 2 | 3 | 6
|  | There are measures in place to limit smoking to specific, well-ventilated areas. | NOT APPLICABLE | 2 | 2 | 4
|  | There are tip lines and other communication methods set up to report instances of unsafe behaviour. | NOT APPLICABLE | 2 | 1 | 2
|  | There is enhanced monitoring in place (additional security guards, surveillance cameras) to monitor for unsafe behaviour. | NOT APPLICABLE | 2 | 2 | 4
| Non Infectious Disease Health Threats (injuries, stampedes, trampling) | There are plans in place to handle stampedes or other forms of physical violence at the event venue (e.g., fights, riots, etc.). | No | 0 | 3 | 0
Epidemiological Factors | Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns vector borne disease) Non Infectious Disease Health Threats | Daily health screening will be conducted for entrance into the mass gathering. | Yes | 2 | 1 | 2
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns vector borne disease) Non Infectious Disease Health Threats | Measures will be in place to promote physical distancing. | No | 0 | 3 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns vector borne disease) Food Safety and/or Clean Water Concerns | Mask use will be strongly recommended. | No | 0 | 2 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) | Mask use will be required. | No | 0 | 3 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns vector borne disease) Food Safety and/or Clean Water Concerns | If there is an outbreak, vaccination against the disease will be strongly recommended. | No | 0 | 2 | 0
| Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs) Epidemiological Concerns vector borne disease) | If there is an outbreak, vaccination against the disease will be required. | No | 0 | 3 | 0
|  | Testing programmes for STIs will be available. | No | 0 | 2 | 0
|  | Testing programmes for identified diseases of concern will be available. | No | 0 | 2 | 0
|  | If there is an outbreak of an identified disease, proof of a negative test will be strongly recommended. | No | 0 | 2 | 0
|  | If there is an outbreak of an identified disease, proof of a negative test will be required. | No | 0 | 3 | 0
|  | Measures will be in place to avoid crowding at choke points (such as staggered entry times, etc). | No | 0 | 3 | 0
|  | There are plans in place to conduct health screenings at official points of entry or border checkpoints for participants and spectators from other countries. | No | 0 | 2 | 0
|  | There are sufficient medical staff at the venue to provide physical and mental first aid. | No | 0 | 2 | 0
|  | There are plans in place to transport sick or injured attendees to offsite medical facilities. | No | 0 | 1 | 0
|  | There are sufficient capacities to handle increased laboratory testing during the event. | No | 0 | 1 | 0
|  | There are plans or protocols in place to rapidly acquire and dispense medical and non-medical countermeasures (i.e., drugs, vaccines, diagnostic tests, personal protective equipment, prophylactics, etc.) on a mass scale. | No | 0 | 2 | 0
|  | There is sufficient space, personnel, and equipment to implement quarantine, isolation, and/or decontamination protocols. | No | 0 | 2 | 0
|  | Relevant response plans and protocols have been regularly tested and/or exercised prior to the event. | Yes | 2 | 3 | 6
CBRN and Other Security Factors | CBRN threats | There is monitoring of media and communication channels for CBRN related threats. | Yes | 2 | 2 | 4
|  | There are dedicated safety protocols in place to respond to an attack that occurs during the event, including detailed evacuation and medical plans for participants. | Yes | 2 | 3 | 6
|  | A threat analysis of the event has been conducted to identify the potential risks and mitigate them. | No | 0 | 3 | 0
|  | Security measures are in place to reduce the risk of weapons being brought into the venue (such as bag checks and metal detectors at points of entry). | No | 0 | 3
| CBRN threats | Mass gathering event organizers are liaising with relevant security, intelligence and law enforcement on CBRN threats. | NOT APPLICABLE | 2 | 2 | 4
|  | Local law enforcement, emergency management, public health, and other public safety officials have been notified of the event. | No | 0 | 1 | 0
|  | There are protocols in place to coordinate response efforts with local law enforcement, emergency management, public health, and other public safety officials during a large-scale emergency (e.g., fire, CBRN event, stampede, etc.) requiring mass evacuation, mitigation, and/or decontamination. | INFO UNAVAILABLE | 1 | 2 | 2
|  | There are protocols in place to coordinate with law enforcement and/or the intelligence community to investigate deliberate events (e.g., arson, shootings, CBRN events, etc.) at the venue. | Yes | 2 | 2 | 4
Environmental Factors | Epidemiological Concerns (vector borne disease) | There are sufficient pest and vector control capacities in place (e.g., provision of insect repellent, removal of standing water, fumigation, etc.). | Yes | 2 | 3 | 6
| Epidemiological Concerns (vector borne disease) Food Safety and/or Clean Water Concerns | There are capacities in place to monitor the safety of local water supplies. | No | 0 | 3 | 0
| Food Safety and/or Clean Water Concerns | There are restrooms and/or handwashing stations available at the venue. | Yes | 2 | 2 | 4
|  | Those responsible for handling food at the event be required to wash their hands and wear a mask prior to and during food preparation. | Yes | 2 | 2 | 4
|  | There be sanitation and waste checks at the venue/s. | NO | 0 | 2 | 0
| Epidemiological Concerns (vector borne disease) Non Infectious Disease Health Threats (injuries, stampedes, trampling) Extreme Weather Condition Concerns (frostbite, over heating) Food Safety and/or Clean Water Concerns | There are trash removal services available at the venue. | NOT APPLICABLE | 2 | 2 | 4
| Extreme Weather Condition Concerns (frostbite, over heating) | There are plans or protocols in place to transition the gathering to an indoor venue in the event of severe weather (e.g., storms, flooding, wildfires, extreme cold or heat, etc.). | NO | 0 | 2 | 0
| Extreme Weather Condition Concerns (frostbite, over heating) | There are warming or cooling centers in place for outdoor activities. | NO | 0 | 2 | 0
|  | WHO/2023-Generic/Mass_gatherings_All_Hazards_RAtool/2023.1 |  |  |  | 94
| © WHO 2022. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence. | © WHO 2023. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence. |  |  |  | 33.3333
Note on C7: WANG, Ninglan: Not clear about the logics of this column-- how these three rows correspond to 10 rows in the liklihood of migigation statement. Also, why the row 8 and 9 are the same and partially different from row 7
Note on C35: WANG, Ninglan: Same with my comment above, it needs to be restructured -- the first 10 rows are the same can be grouped. Also, clarification needs to be provided why row 32 adding food safety and clean water speaks to indoor temperature

## 2C. Risk Score
Step 2C: Risk Score
The questions and statements assessed in Steps 1, 2A & 2B are combined to determine the Risk Score of the mass gathering, depending on the hazards identified, their likelihood of occurring and the impact should they occur. The Risk Score is determined by a risk matrix combining the likelihood and impact of the pre-identified hazards.
Risk Matrix
238.5-294.5 | Hazard Score | Critical | LOW | MODERATE | HIGH | VERY HIGH | VERY HIGH |  |  | Key
175.5-238 |  | Severe | LOW | MODERATE | HIGH | HIGH | VERY HIGH |  |  | Very High
102.5-175 |  | Moderate | VERY LOW | LOW | MODERATE | HIGH | HIGH |  |  | High
40-102 |  | Minor | VERY LOW | VERY LOW | LOW | MODERATE | MODERATE |  |  | Moderate
0-39.5 |  | Negligable | VERY LOW | VERY LOW | VERY LOW | LOW | LOW |  |  | Low
|  |  | Very Unlikely | Unlikely | Likely | Very Likely | Almost Certain |  |  | Very Low
Likelihood Score
|  |  | 86-100 | 66-85 | 36-65 | 16-35 | 0-15
| Hazard Score |  |  | MODERATE |  |  |  | 148 | MODERATE
| Likelihood Score |  |  | VERY LIKELY |  |  |  | 33.3333 | VERY LIKELY
| Overall Risk Assessment Score |  |  | HIGH
WHO/2023-Generic/Mass_gatherings_All_Hazards_RAtool/2023.1
© WHO 2023. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.

## 2D. Determining Impact
Step 2D: Determining the Impact to the Health System if the Hazard Occurs
What are the impact should a hazard occur during the mass gathering and what is the ability of the host country to respond to such a hazard to mitigate further negative health outcomes? Considerations include severity of the hazard occurring, vulnerability of the population, and local coping capacity.
Instuctions: Select the country where the mass gathering will be taking place. If there a multiple countries, you must conduct a risk assessment per country. Please use the link below to access the host country's SPAR score then fill in the reported score for each of indicator. If the SPAR scores are older than 2 years, or if there is no SPAR score, you must answer the additional statements below ("Estimation of Capacities").
Where will the mass gathering take place (select a country)? | Antigua and Barbuda |  |  | Scoring System
|  |  |  | Indicator Level | Score | Score Range | Color
Category | Impact or Country Capacity Question | Answer or Score |  | 1 | 20 | 0-20 |  | Low
States Parties Self-Assessment Annual Reporting (SPAR) | Has the country completed a self-assessment annual report using the States Parties Self-Assessment Annual Reporting (SPAR) tool? If YES, please enter the most recent available country scores for the following SPAR indicators (available to download here). |  |  | 2 | 40 | 21-40 |  | Medium
| C4.1 Specimen referral and transport system |  |  | 3 | 60 | 41-60 |  | Medium
| C4.2. Implementation of a laboratory biosafety and biosecurity regime |  |  | 4 | 80 | 61-80 |  | High
| C4.3. Laboratory quality system |  |  | 5 | 100 | 81-100 |  | High
C4.4. Laboratory testing capacity modalities
C4.5. Effective national diagnostic network
C5.1. Early warning surveillance function
C5.2. Event management
C7.1. Planning for health emergencies
C7.2. Management of health emergency response
C7.3. Emergency logistic and supply chain management
C8.1. Case management
C8.2. Utilization of health services
C8.3. Continuity of essential health services (EHS)
C10.1. RCCE system for emergencies
C10.2. Risk communication
C10.3. Community engagement
C11.1. Core capacity requirements at all times for PoEs
C11.2. Public health response at PoEs
C11.3. Risk-based approach to international travel-related measures
C13.1 Multisectoral collaboration mechanism for food safety events
C14.1. Resources for detection and alert (chemical events)
C15.1. Capacity and resources (radiation emergencies)
| SPAR Score | 0
SPAR Capacity Result
Estimation of Capacities | Please answer the below questions to provide a rough estimation of the local healthcare capacities. Answer each statement with a High, Medium or Low option, If you do not know - or cannot estimate - what the capacity level is, asnwer DON'T KNOW. To the best of your judgment, please rate the following capacities as HIGH (robust capacity will be in place at the gathering), MEDIUM (middling capacity will be in place at the gathering) or LOW (weak or no capacity will be in place at the gathering).
| Laboratory capacities, including specimen referral and transport systems; laboratory biosafety and biosecurity regimes; quality systems; testing modalities; and a national diagnostic network. | High | 80
| Surveillance capacities, including early warning systems and verification, investigation, analysis, and dissemination of information. | Low | 10
| Health emergency management capacities, including planning for health emergencies; management of health emergency response; and emergency logistic and supply chain management. | Medium | 50
| Health services provision capacities, including case management, health service utilization, and continuity of essential health services. | Medium | 50
| Risk communication and community engagement (RCCE) capacities, including RCCE systems for emergencies; mechanisms for public communication and/or media relations (including infodemics); and guidelines/SOPs for implementing community engagement activities at national and subnational levels. | Low | 10
| Point of entry (PoE) and border health capacities at airports, ports, and ground crossings; public health emergency contingency plans for PoEs; and a national multisectoral process with mechanisms to determine the adoption of international travel-related measures, in a risk-based manner. | High | 80
| Food safety capacities, including a multisectoral collaboration mechanism for addressing foodborne outbreaks. | High | 80
| Mass casualty management capacity which has been exercised (drill or real-life event). | High | 80
| Estimated Capacity Score | 55
| Estimated Capacity Result | Moderate Capacity
Health System Capacity | Moderate Capacity
WHO/2023-Generic/Mass_gatherings_All_Hazards_RAtool/2023.1
© WHO 2023. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.

## 3. Precautionary Measures
Step 3: Identifying the Precautionary Measures to Put into Place and Mitigate Risks
Which mitigation and precautionary measures should you prioritize implementing for you mass gathering?
Instructions: From the mitigation statements identified in Step 2B, insert the precautionary measures and mitigations that will be put into place for your mass gathering and provide their status of implementation. Also provide any notes such as changes to the mitigation measures etc.
Category | Mitigation Measure | Status of Implementation | Notes
General Factors | 1
2
3
4
5
Venue Factors | 1
2
3
4
5
Behavioural Factors | 1
2
3
4
5
Epidemiological Factors | 1
2
3
4
5
CBRN Threats | 1
2
3
4
5
Health System Factors | 1
2
3
4
5
Environmental Factors | 1
2
3
4
5
Coordination with Law Enforcement, Public Health, and Public Safety | 1
2
3
4
5
Miscellaneous | 1
2
3
4
5
WHO/2023-Generic/Mass_gatherings_All_Hazards_RAtool/2023.1
© WHO 2023. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.

## 4. Risk Communication
Step 4: Implementing and Communicating a Mass Gathering Plan
How to effectively implement and communicate a mass gathering plan including developing messaging on decisions and changes to policies to ensure a safe and successful mass gathering.
Instructions: Read through the considerations for risk communication and community engagement as well as infodemic management to build a comprehensive mass gathering communications plan including considerations on messaging various policy decisions and changes ahead of or during the mass gathering.
Misinformation during public health emergencies has been characterized by the surge of information, some true but some false, circulating across communication channels, inundating people with messages and complicating health communication efforts. Given these challenges in the global communication landscape, most individuals at a mass gathering will have some preconceived notions about the public health risks they may face. These perceptions will likely be informed by an individual’s personal experiences, the current state of their home jurisdiction’s response to public health threats, and many other social and political viewpoints. Clear risk communication is essential to helping people accept changes and modifications to how an event is carried out. This is especially important when personal behaviour change is a part of the required changes and modifications.
A robust risk communication strategy for a mass gathering event should be built on two foundational understandings: 1. The rationale behind the mass gathering modifications/changes 2. The communication needs of those at the gathering.
This All-Hazards Mass Gathering Risk Assessment Tool helps identify pathways for safer mass gathering practices, but the rationale for these pathways must be effectively communicated to support successful implementation. The assessment tool can also be a valuable resource for message construction, since the process of decision-making is made more transparent, helping to increase buy-in from the mass gathering participants.
The social, political, and ecological environments in which a mass gathering takes place are highly dynamic, and the gathering’s risk profile could evolve at any time. Therefore, when communicating with stakeholders, event organizers should address this uncertainty upfront, be prepared to explain the impact of unforeseen contingencies on their decision-making process, and acknowledge that further modifications may be needed as the event progresses.
Building a flexible communication strategy, acknowledging uncertainty, and transparency around decision-making processes are essential components of effective risk communication. A risk communication strategy should begin with a needs assessment and identification of proper channels for communication (through partners and community engagement). Such a strategy should also identify influencers who can lend credibility to communication efforts, disseminate information, and ensure that the right information reaches target audiences. Event planners must also be prepared to monitor and manage rumours and misinformation, as well as evaluate the effectiveness of risk communication efforts to inform future work.
The “Evaluating the Likelihood of the Hazard Occuring” section (Step 2B) of the Generic All-Hazards Risk Assessment Tool for Mass Gathering Events has translated a number of these strategy elements into actionable steps designed to guide your modification efforts. You can use these questions, as well as others covered in this section, to begin developing a risk communication strategy for your mass gathering event.
If your organization is looking for assistance, national health offices may be able to provide services to inform risk communication strategies. Additionally, there are a number of free resources that can inform these efforts, including the WHO publications listed below.
Checklist for Effectively Implementing and Communicating Your Mass Gathering Plan When disseminating your mass gathering plan, have you considered the following?
WHO Resource Links: - Risk Communication Essentials - Training (https://openwho.org/courses/risk-communication) - Communication Risk in Public Health Emergencies Guideline (https://www.who.int/publications/i/item/communicating-risk-in-public-health-emergencies) - Risk Communication: Frequently Asked Questions (https://www.who.int/news-room/q-a-detail/risk-communication-frequently-asked-questions)
WHO/2023-Generic/Mass_gatherings_All_Hazards_RAtool/2023.1
© WHO 2023. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.
We have a plan in place to quickly and efficiently provide any changing information or the most up to date information on the mass gathering
We have idenified the different audience groups to share messages related to the mass gathering
We have developed tailored messaging for different audience groups with appropriate language and clear information on the mass gathering plan
We have engaged with different stakeholders to ensure the language used and decisions made in the mass gathering plan are inclusive to all
We have shared the mass gathering plan and other relevant information through a variety of platforms and messaging services
We have ensured there are pathways for members of the public, staff, mass gathering attendees and other stakeholders to ask questions or provide comments to event organizers and health authorities

## Reviewer Sign Off
WHO Mass Gathering All Hazard Risk Assessment Tool - Sign Off Page
Hazard Score |  |  |  | MODERATE | 0 | 0 | 0
Likelihood Score |  |  |  | VERY LIKELY | 0 | 0 | 0
Overall Risk Assessment Score |  |  |  | HIGH | 0 | 0 | 0
Country Capacity Score |  |  |  | Moderate Capacity
Reviewer Comments:
Reviewer Signatures:
Number | Name | Affiliation | Signature
1
2
3
4
5
6
7
8
9
10
WHO/2023-Generic/Mass_gatherings_All_Hazards_RAtool/2023.1
© WHO 2023. Some rights reserved. This work is available under the CC BY-NC-SA 3.0 IGO licence.

## Back end 2 (hidden)
WHO Regions
Africa
Americas
South-East Asia | [10 empty] | Epidemiological Concerns (infectious disease outbreaks from person to person spread, not including STIs)
Europe | [10 empty] | Epidemiological Concerns (STIs)
Eastern Mediterranean | [10 empty] | Epidemiological Concerns (vector borne disease)
Western Pacific | [10 empty] | Non Infectious Disease Health Threats (injuries, stampedes, trampling)
Extreme Weather Condition Concerns (frostbite, over heating)
CBRN threats
YES |  |  | WEAK | [7 empty] | Food Safety and/or Clean Water Concerns
NO |  |  | FAIR |  | Less than 1
NOT APPLICABLE |  |  | STRONG |  | 1 to <3
INFO UNAVAILABLE |  |  |  |  | 3 to <5
|  |  | NO |  | 5 to <7 |  |  |  | HIGH RISK
YES |  |  | LIMITED CAPACITIES |  | Greater than 7 |  |  |  | MODERATE RISK
NO |  |  | DEVELOPED BUT NOT TESTED | [5 empty] | LOW RISK
INFO UNAVAILABLE |  |  | DEMONSTRATED CAPACITY | [5 empty] | INSIGNIFICANT
[9 empty] | INFO UNAVAILABLE |  |  | Very Unlikely
NO CASES | [8 empty] | NOT APPLICABLE |  |  | Unlikely
SPORADIC CASES | [11 empty] | Likely
CLUSTERS OF CASES | [11 empty] | Very Likely
COMMUNITY TRANSMISSION | [11 empty] | Almost Certain
Public transportation (e.g., metro or subway, bus, etc.)
|  |  |  | YES - IN VENUES WITH POOR VENTILATION | [5 empty] | Private transportation (e.g., personal vehicles, rideshares, taxis, flights)
LESS THAN 25% |  |  |  | YES - IN VENUES WITH GOOD VENTILATION PRACTICES | [5 empty] | Transportation provided by the event organizers (e.g., shuttles)
25-50% |  |  |  | NO | [5 empty] | Other
51-75% |  |  |  | INFO UNAVAILABLE | [5 empty] | A mixture of the above
GREATER THAN 75%
INFO UNAVAILABLE |  |  | Does not report any vaccine rates or seroprevelance levels |  |  |  |  | Event-Provided Transportation
NOT APPLICABLE |  |  | Less than 1% |  |  |  |  | No Transportation Has Been Organized
|  |  | 1-10% |  |  |  |  | Not Applicable
|  |  | >10-20% |  |  |  |  | Info Unavailable
WEAK |  |  | >20-30% |  |  |  | Sporting or athletic event (e.g., match, tournament, exhibition)
FAIR |  |  | >30-40% |  |  |  | Performing arts event (e.g., musical, theatrical, or other stage production)
STRONG |  |  | >40-50% |  |  |  | Religious event (e.g., worship service, pilgrimage, festival)
|  |  | >50-60% |  |  |  | Conference, exposition, or fair
|  |  | >60-70% |  |  |  | Unstructured gathering (e.g. informal congregation at parks, beaches, bars/restaurants, or other public spaces)
LESS THAN 1 |  |  | >70-80% |  |  |  | Other
1 to 2 |  |  | >80-90%
3 to 5 |  |  | >90%
6 to 10 |  |  | NOT APPLICABLE
11 to 15 | [6 empty] | Indoors
16 to 20 | [6 empty] | Outdoors
21 OR ABOVE | [6 empty] | Virtually
Indoors and outdoors
Hybrid format (i.e., virtually and in-person)
YES, LESS THAN 25% |  |  | LESS THAN 25% |  |  |  | Don’t know
YES, BETWEEN 25-50% |  |  | BETWEEN 25% - 50%
YES, BETWEEN 51-75% |  |  | BETWEEN 51% - 75%
YES, GREATER THAN 75% |  |  | GREATER THAN 75%
YES, PROPORTION IS UNKNOWN |  |  | PROPORTION IS UNKNOWN |  |  |  | Local attendees
NO |  |  | NOT APPLICABLE |  |  |  | National attendees
INFO UNAVAILABLE | [6 empty] | International attendees
NOT APPLICABLE | [6 empty] | All of the above
Don’t know
<1 hour
|  |  |  | 1-3 hours |  |  | Recreational or illicit substance use (including injectable drugs)
|  | <100 |  | < 1 day |  |  | Alcohol consumption
|  | 100-1,000 |  | < 1 week |  |  | Unprotected sexual intercourse
|  | 1,000-10,000 |  | <1 month |  |  | Physical violence or self-harm
|  | 10,000-100,000 |  | > 1 month |  |  | Fasting or other dietary modifications
|  | >100,000 |  |  |  |  | A mixture of the above
Convening in close proximity to one another for extended periods of time
Singing, cheering, chanting, or other forms of collective vocalization
A mixture of the above
Diphtheria
Tetanus
Hepatitis A |  |  | Rotavirus | Chikungunya |  | HIV/AIDS |  | COVID-19 |  | Cancer
Hepatitis B |  |  | Norovirus | Dengue fever |  | Syphilis |  | Seasonal influenza |  | Cardiovascular disease
Measles |  |  | Cholera | Lymphatic filariasis |  | Chlamydia |  | Tuberculosis |  | Diabetes
Mumps |  |  | E. coli | Rift Valley fever |  | Gonorrhea |  | Don’t know |  | Chronic kidney disease
Rubella |  |  | Salmonella | Yellow fever |  | Don’t know |  |  |  | Chronic respiratory disease (e.g., COPD)
Hib disease |  |  | Don’t know | Zika virus disease | [5 empty] | Obesity
Meningococcal disease |  |  |  | Lymphatic filariasis | [5 empty] | Malnutrition
Human papillomavirus |  |  |  | Malaria | [5 empty] | Don't Know
Pneumococcal disease |  |  |  | Japanese encephalitis
Rabies |  |  |  | West Nile fever
Chickenpox |  |  |  | Schistosomiasis
Whooping cough (pertussis) |  |  |  | Onchocerciasis (river blindness)
Respiratory syncytial virus (RSV) |  |  |  | Plague
Don’t know |  |  |  | Tungiasis
Typhus
Louse-borne relapsing fever
Leishmaniasis
Sandfly fever
Crimean-Congo haemorrhagic fever
Lyme disease
Relapsing fever (borreliosis)
Rickettsial diseases (e.g., spotted fever, Q fever)
Tick-borne encephalitis
Tularaemia
Chagas disease
Sleeping sickness
Don’t know
Afghanistan
Albania
Algeria
Andorra
Angola
Antigua and Barbuda
Argentina
Armenia
Australia
Austria
Azerbaijan
Bahamas
Bahrain
Bangladesh
Barbados
Belarus
Belgium
Belize
Benin
Bhutan
Bolivia (Plurinational State of)
Bosnia and Herzegovina
Botswana
Brazil
Brunei Darussalam
Bulgaria
Burkina Faso
Burundi
Cabo Verde
Cambodia
Cameroon
Canada
Central African Republic
Chad
Chile
China
Colombia
Comoros
Congo
Cook Islands
Costa Rica
Cote d'Ivoire
Croatia
Cuba
Cyprus
Czech Republic
Czechoslovakia (former)
Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
Djibouti
Dominica
Dominican Republic
Ecuador
Egypt
El Salvador
Equatorial Guinea
Eritrea
Estonia
Eswatini
Ethiopia
Fiji
Finland
France
Gabon
Gambia
Georgia
Germany
Germany, Democratic Republic (former)
Germany, Federal Republic (former)
Germany, West Berlin (former)
Ghana
Greece
Greenland
Grenada
Guadeloupe (until 2003)
Guatemala
Guinea
Guinea-Bissau
Guyana
Haiti
Honduras
Hungary
Iceland
India
India (until 1975)
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kiribati (until 1984)
Kuwait
Kyrgyzstan
Lao People's Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libya
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia (Federated States of)
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
Netherlands Antilles (from 1986 until 2010)
Netherlands Antilles (until 1985)
New Zealand
Nicaragua
Niger
Nigeria
Niue
North Macedonia
Norway
Occupied Palestinian Territory
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Puerto Rico
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Serbia and Montenegro (2003-2006)
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
South Sudan
South Viet Nam (former)
Spain
Sri Lanka
State Union of Serbia and Montenegro (1993-2002)
Sudan
Sudan (until 2011)
Suriname
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
Timor-Leste
Togo
Tokelau
Tonga
Trinidad and Tobago
Tunisia
Türkiye
Turkmenistan
Tuvalu
Uganda
Ukraine
Union of Soviet Socialist Republics (former)
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela (Bolivarian Republic of)
Viet Nam
Yemen
Yemen Arab Republic (until 1990)
Yugoslavia, Socialist Federal Republic (until 1992)
Zambia
Zimbabwe
Other/ Not a WHO Member State